## Gantt Chart
MWD Enterprise Cybersecurity Program — 12-Month Project Plan (Gantt Chart)
Project Start Date (edit this cell to reschedule the entire plan): | [5 empty] | 2026-08-03 | <- input | Durations = business days (WORKDAY calendar, no holidays). A phase's tasks cannot start until every task in the prior phase finishes (same small team runs every phase). This CPM schedule reflects task effort only - no procurement/holiday buffer - so it converges faster than a calendar-driven 12-month reporting cadence; treat the Strategy document's Section 9 as the governance calendar and this sheet as the underlying technical schedule.
P0 Foundation |  | P1 Identity/Data |  | P2 Detection/Response |  | P3 Cloud/OT |  | P4 Optimization
ID | Task Name | Phase | Duration (Bus. Days) | Pred. | Resource Names | Deliverable | Success Criteria | Start Date | Finish Date | Phase Code | Prior Phase End | 2026-08-03 | 2026-09-03 | 2026-10-03 | 2026-11-03 | 2026-12-03 | 2027-01-03 | 2027-02-03 | 2027-03-03 | 2027-04-03 | 2027-05-03 | 2027-06-03 | 2027-07-03
1 | Program kickoff and governance charter | P0 - Foundation (M1) | 5 |  | CISO, Cybersecurity Manager | Signed program charter and RACI | Charter approved by executive sponsor | 2026-08-03 | 2026-08-07 | 1 | 0
2 | MDR/24x7 SOC augmentation - procurement | P0 - Foundation (M1) | 10 | 1 | CISO | Signed MDR contract (Falcon Complete/OverWatch) | Contract executed; onboarding scheduled | 2026-08-10 | 2026-08-21 | 1 | 0
3 | MDR onboarding and integration with CrowdStrike/QRadar | P0 - Foundation (M1) | 10 | 2 | Cybersecurity Manager, Threat Analysts | 24x7 monitoring live | MDR provider actively triaging alerts | 2026-08-24 | 2026-09-04 | 1 | 0
4 | Backup immutability assessment and remediation | P0 - Foundation (M1) | 10 | 1 | Network Specialist | Immutable/air-gapped backup confirmed for Tier-1 systems | Object-lock or air-gap verified on backup repository | 2026-08-10 | 2026-08-21 | 1 | 0
5 | Security awareness training platform deployment | P0 - Foundation (M1) | 10 | 1 | GRC Consultants | Awareness platform live org-wide | 100% of users enrolled; first phishing simulation scheduled | 2026-08-10 | 2026-08-21 | 1 | 0
6 | OT/ICS security vendor assessment (Claroty/Dragos/Nozomi) | P0 - Foundation (M1) | 15 | 1 | CISO, Network Specialist | Vendor shortlist and selection | Vendor selected; SOW drafted | 2026-08-10 | 2026-08-28 | 1 | 0
7 | Confirm M365 E5/Entra ID P2 licensing | P0 - Foundation (M1) | 5 | 1 | Cybersecurity Manager | Licensing confirmation memo | Licensing gaps identified and remediated | 2026-08-10 | 2026-08-14 | 1 | 0
8 | Enforce phishing-resistant MFA for privileged accounts | P0 - Foundation (M1) | 10 | 7 | Cybersecurity Manager | MFA enforced for all privileged accounts | 100% privileged account MFA coverage | 2026-08-17 | 2026-08-28 | 1 | 0
9 | Advanced email security pilot (Proofpoint/Mimecast/Abnormal) | P1 - Identity & Data Protection (M2-3) | 15 | 3 | Network Specialist | Email security pilot live for high-risk mailboxes | Pilot mailboxes protected; false-positive rate acceptable | 2026-09-07 | 2026-09-25 | 2 | 2026-09-04
10 | DLP policy design (Microsoft Purview) | P1 - Identity & Data Protection (M2-3) | 15 | 7 | GRC Consultants, Cybersecurity Manager | DLP policy draft | Policy reviewed and approved by data owners | 2026-09-07 | 2026-09-25 | 2 | 2026-09-04
11 | Secrets management pilot (Vault/CyberArk Conjur) | P1 - Identity & Data Protection (M2-3) | 15 | 8 | Network Specialist | Secrets vaulting pilot for top 10 applications | Pilot applications no longer use hardcoded credentials | 2026-09-07 | 2026-09-25 | 2 | 2026-09-04
12 | Advanced email security full rollout | P1 - Identity & Data Protection (M2-3) | 10 | 9 | Network Specialist | Email security live org-wide | 100% mailbox coverage | 2026-09-28 | 2026-10-09 | 2 | 2026-09-04
13 | DLP policy rollout | P1 - Identity & Data Protection (M2-3) | 15 | 10 | Cybersecurity Manager | DLP enforced across email/SharePoint/Teams/endpoint | DLP incidents logged and triaged in SIEM | 2026-09-28 | 2026-10-16 | 2 | 2026-09-04
14 | PAM depth enhancement (JIT, session recording) | P1 - Identity & Data Protection (M2-3) | 20 | 8 | Cybersecurity Manager | Enhanced PAM configuration live | 100% privileged sessions recorded | 2026-09-07 | 2026-10-02 | 2 | 2026-09-04
15 | Vulnerability management platform deployment (Tenable/Rapid7) | P1 - Identity & Data Protection (M2-3) | 15 | 7 | Cybersecurity Manager, Network Specialist | VM platform deployed and scanning | Full IT asset scan coverage achieved | 2026-09-07 | 2026-09-25 | 2 | 2026-09-04
16 | Vulnerability management SLA policy finalization | P1 - Identity & Data Protection (M2-3) | 10 | 15 | CISO, GRC Consultants | Signed VM SLA policy | Policy signed by executive leadership | 2026-09-28 | 2026-10-09 | 2 | 2026-09-04
17 | First full vulnerability baseline report | P1 - Identity & Data Protection (M2-3) | 5 | 15 | Cybersecurity Manager | Baseline vulnerability report | Report delivered to CISO | 2026-09-28 | 2026-10-02 | 2 | 2026-09-04
18 | SOAR platform deployment (Cortex XSOAR/QRadar SOAR) | P2 - Detection & Response (M4-6) | 20 | 3 | Threat Analysts, Cybersecurity Manager | SOAR live and integrated with QRadar | SOAR ingesting SIEM alerts | 2026-10-19 | 2026-11-13 | 3 | 2026-10-16
19 | SOAR playbook development (phishing/isolation/IOC blocklist) | P2 - Detection & Response (M4-6) | 15 | 18 | Threat Analysts | 3 production playbooks | Playbooks handling live Tier-1 alerts | 2026-11-16 | 2026-12-04 | 3 | 2026-10-16
20 | Threat intelligence platform integration (WaterISAC + commercial feed) | P2 - Detection & Response (M4-6) | 15 | 18 | Threat Analysts | TIP integrated into QRadar/SOAR | IOC feed actively enriching alerts | 2026-11-16 | 2026-12-04 | 3 | 2026-10-16
21 | CASB/SSPM deployment | P2 - Detection & Response (M4-6) | 15 | 13 | Network Specialist | SaaS posture monitoring live | Baseline SaaS posture report delivered | 2026-10-19 | 2026-11-06 | 3 | 2026-10-16
22 | Attack surface management tool deployment | P2 - Detection & Response (M4-6) | 10 | 6 | Network Specialist | External ASM baseline established | Baseline external exposure report delivered | 2026-10-19 | 2026-10-30 | 3 | 2026-10-16
23 | DLP rollout completion beyond pilot | P2 - Detection & Response (M4-6) | 10 | 13 | Cybersecurity Manager | DLP fully enforced org-wide | All defined data categories covered | 2026-10-19 | 2026-10-30 | 3 | 2026-10-16
24 | IR plan and runbook formalization | P2 - Detection & Response (M4-6) | 15 | 1 | CISO, Cybersecurity Manager | Signed IR plan and runbooks | IR plan approved by executive leadership | 2026-10-19 | 2026-11-06 | 3 | 2026-10-16
25 | Retained DFIR firm contract | P2 - Detection & Response (M4-6) | 15 | 24 | CISO | Signed DFIR retainer contract | Retainer active and contacts documented | 2026-11-09 | 2026-11-27 | 3 | 2026-10-16
26 | First tabletop exercise (ransomware scenario) | P2 - Detection & Response (M4-6) | 5 | 24 | CISO, Cybersecurity Manager, Threat Analysts | Tabletop after-action report | Findings documented and remediation tracked | 2026-11-09 | 2026-11-13 | 3 | 2026-10-16
27 | OT/ICS monitoring platform deployment - wave 1 sites | P3 - Cloud & OT Security (M7-9) | 25 | 6 | Network Specialist, Threat Analysts | OT monitoring live at wave 1 facilities | OT asset inventory v1 delivered | 2026-12-07 | 2027-01-08 | 4 | 2026-12-04
28 | OT/ICS alert integration into QRadar | P3 - Cloud & OT Security (M7-9) | 10 | 27 | Threat Analysts | OT alerts visible in SIEM | OT alerts triaged through existing SOC workflow | 2027-01-11 | 2027-01-22 | 4 | 2026-12-04
29 | IT/OT segmentation project (Panorama/ISE boundary enforcement) | P3 - Cloud & OT Security (M7-9) | 25 | 27 | Network Specialist, CISO | Segmentation implemented at wave 1 sites | No direct OT-to-internet paths; segmentation validated | 2027-01-11 | 2027-02-12 | 4 | 2026-12-04
30 | Vendor remote access brokered through PAM | P3 - Cloud & OT Security (M7-9) | 10 | 29 | Network Specialist | Vendor remote access policy enforced | No standing VPN credentials for OT vendors | 2027-02-15 | 2027-02-26 | 4 | 2026-12-04
31 | CNAPP/CSPM deployment | P3 - Cloud & OT Security (M7-9) | 15 | 21 | Network Specialist | Cloud posture baseline established | Misconfigurations tracked and remediated | 2026-12-07 | 2026-12-25 | 4 | 2026-12-04
32 | PKI/certificate lifecycle management deployment | P3 - Cloud & OT Security (M7-9) | 15 | 1 | Network Specialist | Certificate inventory and expiry alerting live | Zero unplanned cert-expiry outages | 2026-12-07 | 2026-12-25 | 4 | 2026-12-04
33 | Purple team exercise | P3 - Cloud & OT Security (M7-9) | 10 | 19 | CISO, Threat Analysts | Purple team after-action report | Detection gaps identified and remediated | 2026-12-07 | 2026-12-18 | 4 | 2026-12-04
34 | NIST 800-53 control validation cycle | P4 - Optimization & Assurance (M10-12) | 15 | 17 | GRC Consultants | Control validation report | Residual gap list produced | 2027-03-01 | 2027-03-19 | 5 | 2027-02-26
35 | CIS Controls self-assessment | P4 - Optimization & Assurance (M10-12) | 15 | 34 | GRC Consultants | CIS self-assessment report | Assessment scored and documented | 2027-03-22 | 2027-04-09 | 5 | 2027-02-26
36 | Quarterly access recertification | P4 - Optimization & Assurance (M10-12) | 10 | 14 | GRC Consultants | Access recertification sign-off | All privileged/sensitive-data roles recertified | 2027-03-01 | 2027-03-12 | 5 | 2027-02-26
37 | External penetration test (IT and OT scope) | P4 - Optimization & Assurance (M10-12) | 15 | 29 | CISO, external pen-test firm | Penetration test report | Findings tracked to remediation | 2027-03-01 | 2027-03-19 | 5 | 2027-02-26
38 | Full-scale DR test including immutable backup restore | P4 - Optimization & Assurance (M10-12) | 10 | 4 | Network Specialist, Cybersecurity Manager | DR test after-action report | Successful full recovery within RTO/RPO targets | 2027-03-01 | 2027-03-12 | 5 | 2027-02-26
39 | AWIA re-certification readiness check | P4 - Optimization & Assurance (M10-12) | 10 | 34 | GRC Consultants | Readiness assessment memo | Gaps closed prior to re-certification window | 2027-03-22 | 2027-04-02 | 5 | 2027-02-26
40 | Security program maturity review | P4 - Optimization & Assurance (M10-12) | 10 | 37 | CISO | Program maturity report | Maturity score improvement documented vs. baseline | 2027-03-22 | 2027-04-02 | 5 | 2027-02-26
41 | Policy review and refresh (all security policies) | P4 - Optimization & Assurance (M10-12) | 10 | 34 | GRC Consultants | Updated policy set | All policies reviewed within 12 months | 2027-03-22 | 2027-04-02 | 5 | 2027-02-26
42 | Board/executive annual report | P4 - Optimization & Assurance (M10-12) | 5 | 40 | CISO | Annual report presented to leadership/board | Report delivered and accepted | 2027-04-05 | 2027-04-09 | 5 | 2027-02-26
43 | Year 2 roadmap draft | P4 - Optimization & Assurance (M10-12) | 10 | 40 | CISO | Year 2 roadmap document | Roadmap approved by executive sponsor | 2027-04-05 | 2027-04-16 | 5 | 2027-02-26
Formulas:
P4 Optimization = IF(AND([P2 Detection/Response]="",L5=0),G2,WORKDAY(MAX(IFERROR(INDEX(J5:J47,MATCH([P2 Detection/Response],A5:A47,0)),0),L5),1))